## Sheet1
Proposed Role Assignment – Predict Podcast Listening Time
Team Member | Role | Main Responsibilities
Joe Miranda | Project Lead | Organize schedule and meetings, track progress, compile results, interpret feature importance, help finalize conclusions.
Huilin Zhang | Data Lead | Clean and explore dataset, handle missing values/outliers, create descriptive plots, document feature statistics.
Luis Chavez | Feature Lead | Transform or scale features, engineer new features, prepare dataset for modeling, support Data Lead.
Yen Tung Lin | Model Lead | Build baseline regression, test other models (e.g., decision tree, random forest), tune parameters.
Lcndr Aquino | Evaluation Lead | Evaluate models (RMSE/MAE), compare results, lead report writing for methods and results, support presentation.
A role lead is not the only person performing that task. They will solicit assistance from the rest of the team to complete their portion.
Everyone will contribute to the final report and presentation slides
Project Timeline & Milestones - Will revise
Week | Primary Leads | Milestones / Tasks
Week 6a | Huilin | Finish data cleaning; push clean dataset to GitHub
Week 6b | Joe | Review TA’s GitHub example; finalize folder structure & roles
Week 7 | Luis | Complete correlation and feature analysis
Week 8 | Yen & Lcndr | Build baseline + advanced models; start tuning
Week 9 | All | Compare results, finalize visuals, and draft report sections
Week 10 | Joe (with full team) | Edit, merge, and rehearse presentation
Action Items: | Details | Due by:
Huilin Zhang | Download and review project data | Done
Yen Tung Lin | Research possible analysis model for data | Done
Joe Miranda | Check with TA /Professor on direction for Project /Report | Done
Lcndr Aquino | Research possible models to analyze for data | Done
Luis Chavez | Download and review project data | Done
Joe Miranda | Report back direction to team | Done
All | Wait for direction on how to complete project | Never?
Yen Tung Lin | Finish modeling for data set | 2025-10-24
Luis Chavez | Finish feature engineering | 2025-10-24
Joe Miranda | Start compiling presentation deck | 2025-10-24
Lcndr Aquino | ???